## Slide 1
UNIT II · SOFTWARE PROJECT PLANNING
Risk Management
Software Risks • Types of Risk • Risk Assessment • Risk Control
A detailed study of software risk identification, assessment and control, prepared with reference to standard software engineering texts.

## Slide 2
ROADMAP
What We Will Cover
01
Introduction to Risk Management
Why software projects need formal risk handling
02
Software Risk — Definition & Nature
Uncertainty, loss and the concept of risk exposure
03
Types of Risk
Project, technical and business risk; known, predictable, unpredictable
04
Risk Management Activities
Risk assessment and risk control explained in detail
05
Risk Assessment
Identification, analysis/projection and prioritisation of risks
06
Risk Control
RMMM planning, mitigation, monitoring and management
Unit II | Software Project Planning – Risk Management
2

## Slide 3
INTRODUCTION
Why Software Projects Need Risk Management
Software projects operate under constant uncertainty — requirements change, technology evolves, teams shift, and schedules slip.
A risk is a potential problem that may or may not occur in the future; if it does occur, it can adversely affect cost, schedule, quality, or the very success of the project.
Risk management is a proactive strategy: it deals with problems before they occur, rather than reacting after damage is done.
Boehm (1991) summarised it as: “Identify risk before it becomes a problem, and manage it so it never does.”
It is a continuous, iterative activity carried out throughout the software life cycle — from planning to delivery — not a one-time exercise at project start.
Effective risk management improves the probability of a project finishing on time, within budget, and meeting quality expectations.
Unit II | Software Project Planning – Risk Management
3

## Slide 4
DEFINITION
What Is a Software Risk?
Definition
A software risk is defined as an uncertain event or condition that, if it occurs, has a negative effect on a project's objectives — scope, schedule, cost, or quality.
Risk = f(uncertainty, loss). Both elements must be present for a concern to qualify as a risk.
Two Defining Properties
Uncertainty
The risk event may or may not happen. There is never a 100% probability attached to a genuine risk — a certainty is simply a problem, not a risk.
Loss
If the risk becomes a reality, unwanted consequences or losses will occur — in the form of delay, extra cost, degraded quality, or loss of goodwill.
Unit II | Software Project Planning – Risk Management
4

## Slide 5
CORE CONCEPT
Risk Components and Risk Exposure
Every risk is described using three essential components, first identified by Boehm:
  Risk description — a clear statement of what might go wrong (the future condition).
  Risk probability — the likelihood that the situation described will actually occur (0 < p < 1).
  Risk consequence (impact) — the loss or damage that will result if the risk occurs, in terms of cost, schedule, or performance.
These combine to give a quantitative measure called Risk Exposure (RE), also called Risk Impact:
RE = P × C (P = probability of occurrence, C = cost/consequence if it occurs)
Unit II | Software Project Planning – Risk Management
5

## Slide 6
RATIONALE
Importance of Risk Management
Enables early warning: problems are anticipated while there is still time to plan a response, instead of being discovered when it is too late to act.
Improves decision making: project managers can make informed trade-offs between schedule, cost, and scope when risks are quantified.
Reduces the chance of project failure: many documented project failures (cost/schedule overruns, abandonment) can be traced to unmanaged risks.
Improves resource allocation: contingency budget, time buffers, and skilled staff can be directed to the areas of greatest exposure.
Builds stakeholder confidence: a visible risk plan reassures clients and management that the project is under control.
Supports continuous learning: risks realised in one project become checklist items for future projects, improving organisational maturity.
Unit II | Software Project Planning – Risk Management
6

## Slide 7
CLASSIFICATION
Categories of Software Risk
Roger Pressman classifies software risks into three broad categories based on where the risk originates:
Project Risks
Threaten the project plan — budget, schedule, staffing, resources, and customer/requirement problems.
Technical Risks
Threaten the quality and timeliness of the software to be produced — design, implementation, and technology issues.
Business Risks
Threaten the viability of the software once it is built — market, strategic, and management risks.
Unit II | Software Project Planning – Risk Management
7

## Slide 8
TYPES OF RISK · 1 OF 3
Project Risks
Project risks threaten the project plan — if they occur, the project schedule slips and costs increase.
  Budgetary risk — inadequate or fluctuating funding for the project.
  Schedule risk — unrealistic deadlines, delays in deliverables, or dependencies causing slippage.
  Personnel (staffing) risk — insufficient, inexperienced, or high staff-turnover teams.
  Resource risk — non-availability of required hardware, software tools, or facilities.
  Customer risk — changing requirements, poor communication, or lack of customer involvement.
  Requirement risk — requirements that are incomplete, ambiguous, or continually changing (scope creep).
Unit II | Software Project Planning – Risk Management
8

## Slide 9
TYPES OF RISK · 2 OF 3
Technical Risks
Technical risks threaten the quality and timeliness of the software being built; if they occur, implementation may become difficult or impossible.
  Design risk — poor or incomplete design leading to rework during implementation.
  Implementation risk — ambiguous specifications, unproven or immature technology, or difficult algorithms.
  Interfacing risk — problems integrating with other systems, legacy software, or third-party components.
  Verification and validation risk — inadequate test coverage or difficulty in establishing correctness.
  Maintenance risk — software that is difficult to understand, modify, or extend after delivery.
Technical risks are generally more difficult to identify at the outset than project risks, because they are tied closely to the chosen technology and design decisions.
Unit II | Software Project Planning – Risk Management
9

## Slide 10
TYPES OF RISK · 3 OF 3
Business Risks
Business risks threaten the viability of the software once it has been delivered, even if it is built to specification.
  Market risk — building an excellent product that nobody wants because it does not fit market need.
  Strategic risk — building a product that no longer fits the overall business strategy of the organisation.
  Sales/management risk — building a product the sales force does not understand how to sell, or losing management support/commitment.
  Budget risk — losing budgetary or personnel commitment from senior management partway through the project.
These risks are often the hardest to detect early because they depend on external market conditions and internal organisational politics rather than technical facts.
Unit II | Software Project Planning – Risk Management
10

## Slide 11
ALTERNATIVE CLASSIFICATION
Known, Predictable & Unpredictable Risks
Software risks can also be grouped by how easily they can be foreseen:
Known Risks
Risks that can be uncovered after careful evaluation of the project plan, business/technical environment, and other reliable information sources.
e.g. Unrealistic delivery date already fixed in the contract; lack of documented requirements.
Predictable Risks
Risks that are extrapolated from past project experience — they have occurred often enough in similar projects to be expected.
e.g. Staff turnover during a long project; customer requirement changes mid-project.
Unpredictable Risks
Risks that can and do occur, but are extremely difficult to identify in advance using any systematic method.
e.g. Sudden regulatory changes; natural disasters; unforeseen market shifts.
Unit II | Software Project Planning – Risk Management
11

## Slide 12
PROCESS OVERVIEW
Risk Management Activities
Risk management is carried out through two broad, complementary sets of activities:
A. Risk Assessment
Risk identification — recognising possible risks specific to the project.
Risk analysis / projection — estimating probability and impact of each risk.
Risk prioritisation (assessment) — ranking risks so attention goes where it matters most.
B. Risk Control
Risk management planning — deciding strategy and preparing the RMMM plan.
Risk resolution (mitigation) — executing the plan to reduce or eliminate risk.
Risk monitoring — tracking risks and the effectiveness of the plan throughout the project.
Unit II | Software Project Planning – Risk Management
12

## Slide 13
RISK ASSESSMENT · 1
Risk Identification
Risk identification is a systematic attempt to specify threats to the project plan — the first and most important step, since a risk that is never identified can never be managed.
Generic risks — risks that are a potential threat to every software project (e.g. staff turnover, unrealistic schedules).
Product-specific risks — risks identifiable only by those with a clear understanding of the technology, people, and environment specific to the project at hand.
Common technique — a risk item checklist, focused on known and predictable risk categories such as:
  Product size, business impact, customer characteristics, process definition
  Development environment and technology to be built
  Staff size and experience of the project team
Other techniques: brainstorming sessions, Delphi technique, interviews, lessons-learned reviews from past projects, and SWOT analysis.
Unit II | Software Project Planning – Risk Management
13

## Slide 14
RISK ASSESSMENT · 2
Risk Analysis (Risk Projection)
Risk projection (risk estimation) attempts to rate each identified risk in two ways: the likelihood that the risk is real, and the consequence of the problems associated with it.
The project planner, along with other managers and technical staff, performs four risk projection activities:
  Establish a scale that reflects the perceived likelihood of a risk (e.g. probability from 0.1 to 1.0, or a simple Low/Medium/High scale).
  Delineate the consequences of the risk — the impact on cost, schedule, and technical performance.
  Estimate the impact of the risk on the project and product.
  Note the overall accuracy of the risk projection so that there are no misunderstandings.
The output of this analysis feeds directly into the Risk Exposure calculation (RE = P × C) introduced earlier, which is used to compare risks on a common scale.
Unit II | Software Project Planning – Risk Management
14

## Slide 15
RISK ASSESSMENT · 3
Risk Prioritisation — The Risk Table
All identified risks are entered into a risk table, sorted by risk exposure so that the most severe risks are addressed first.
Risk | Category | Probability | Impact (1-5) | RE
Key staff member leaves mid-project | Project | 0.5 | 4 | 2.0
Requirements change frequently | Project | 0.6 | 3 | 1.8
Chosen technology proves immature | Technical | 0.3 | 5 | 1.5
End users resist new system | Business | 0.3 | 4 | 1.2
Third-party component delivered late | Technical | 0.4 | 3 | 1.2
Risk Exposure (RE) = Probability × Impact. Risks above a chosen cut-off line receive an RMMM plan; the rest are monitored only.
Unit II | Software Project Planning – Risk Management
15

## Slide 16
RISK CONTROL · 1
Risk Management Planning — the RMMM Plan
Once risks are analysed and prioritised, the project team develops a strategy for managing risk — documented in a Risk Mitigation, Monitoring and Management (RMMM) Plan.
For each risk above the cut-off line, the plan specifies:
  What can be done to reduce the probability that the risk will occur (mitigation).
  What can be done to reduce the impact if the risk does occur (contingency).
  How the team will know whether the risk is turning into a real problem (monitoring indicators).
  What contingency plans exist if the risk does materialise despite mitigation.
The RMMM plan becomes part of the overall project plan and is reviewed and updated at every project milestone, not written once and forgotten.
Unit II | Software Project Planning – Risk Management
16

## Slide 17
RISK CONTROL · 2
The Three M's — Mitigation, Monitoring, Management
Mitigation
Proactive steps taken to reduce the probability or impact of a risk before it happens.
Add extra staff / cross-train for turnover risk
Conduct technical spikes to retire unproven-technology risk
Freeze requirements after sign-off with a formal change process
Monitoring
Ongoing tracking of factors that provide an indication of whether a risk is becoming more or less likely.
Track team morale and attendance
Track progress against the schedule at each milestone
Watch for early warning signs listed in the RMMM plan
Management
Actions taken assuming that mitigation efforts have failed and the risk has become a real problem.
Execute the pre-planned contingency plan
Reallocate budget / schedule buffers
Escalate to management for a scope or resource decision
Unit II | Software Project Planning – Risk Management
17

## Slide 18
RISK CONTROL · 3
Risk Monitoring in Detail
Risk monitoring is a project-tracking activity performed throughout the project, with three primary objectives:
  Assess whether predicted risks actually occur or not.
  Ensure that risk aversion (mitigation) steps defined for the risk are being properly applied.
  Collect information that can be used for future risk analysis on this and other projects.
The project manager watches for indicators or “factors” such as slipping sub-task completion dates, quality of deliverables falling below expectations, or increasing numbers of change requests.
Where the RMMM steps are documented and tracked, monitoring closes the loop of risk management — feeding results back into risk identification and analysis for the next iteration of the project (or the next project).
Unit II | Software Project Planning – Risk Management
18

## Slide 19
SUMMARY
Key Takeaways
A software risk is an uncertain event that would cause loss if it occurred; Risk Exposure = Probability × Impact.
Risks are classified as project, technical, or business risks (Pressman); or as known, predictable, and unpredictable risks.
Risk management activities fall into two groups: risk assessment (identify, analyse, prioritise) and risk control (plan, resolve/mitigate, monitor).
The RMMM plan documents mitigation, monitoring indicators, and contingency/management actions for every significant risk.
Risk management is continuous — it is revisited at every milestone throughout the software life cycle, not performed once at project start.
Unit II | Software Project Planning – Risk Management
19

## Slide 20
REFERENCES
Books for Reference
Text Books
TB1. K. K. Aggarwal and Yogesh Singh, “Software Engineering”, 3rd Edition, New Age International Publishers, 2008.
TB2. Ian Sommerville, “Software Engineering”, 10th Edition, Pearson Education, 2015.
Reference Books
RB1. Jibitesh Mishra and Ashok Mohanty, “Software Engineering”, Pearson Education, 2011.
RB2. Roger S. Pressman and Bruce R. Maxim, “Software Engineering: A Practitioner's Approach”, 9th Edition, McGraw-Hill Education, 2019.
RB3. James F. Peters and Witold Pedrycz, “Software Engineering: An Engineering Approach”, Wiley India / John Wiley & Sons, 2000.
Unit II | Software Project Planning – Risk Management
20