## Slide 1
SOFTWARE ENGINEERING
Software Project Planning
Metrics, Size Estimation, and Cost Estimation with COCOMO
1 Software Metrics
2 Product / Process / Project Metrics
3 LOC & Function Count
4 Halstead's Software Science
5 COCOMO: Basic & Intermediate

## Slide 2
OVERVIEW
What We Will Cover
01
Software Project Planning
The planning activity and why it matters
02
Software Metrics
Definition, need, and classification
03
Types of Metrics
Product, Process, and Project metrics
04
Size Estimation
Lines of Code (LOC) and Function Point Count
05
Halstead's Software Science
Operators, operands and derived measures
06
Cost Estimation & COCOMO
Need for estimation, Basic and Intermediate models
SOFTWARE PROJECT PLANNING
2

## Slide 3
FOUNDATIONS
Software Project Planning
The first major activity performed by a project manager, undertaken before technical work begins and continued as the project proceeds.
Why planning is essential
Provides a roadmap that defines the tasks and milestones needed to keep a project reasonably on schedule.
Estimates the resources (people, hardware, software) required to complete the work.
Predicts the cost and schedule so that management can commit to realistic delivery dates and budgets.
Reduces risk and uncertainty by identifying problems early, before they become costly.
Forms the basis for monitoring and controlling progress throughout the project life cycle.
Key Planning Tasks
Estimate size / scope of the software
Estimate cost and effort required
Estimate schedule and duration
Identify and plan for risks
Allocate resources and staff
Define metrics for tracking progress
SOFTWARE PROJECT PLANNING
3

## Slide 4
SOFTWARE METRICS
Software Metrics — Definition
A software metric is a quantitative measure of the degree to which a system, component, or process possesses a given attribute — it converts a software characteristic into a number or a rating.
In simple terms
Metrics allow software and the process that produces it to be measured objectively rather than subjectively.
They translate quality attributes such as reliability, maintainability, or complexity into measurable numbers.
Measurement is applied to the software process with the intent of improving it continuously.
Related Terms
Measure: gives a quantitative indication of the extent, amount, dimension or size of an attribute of a product/process. Measurement: the act of determining a measure. Metric: a quantitative measure of the degree to which a system, component or process possesses a given attribute. Indicator: a metric (or a combination of metrics) that provides insight into the software process, project, or product.
SOFTWARE PROJECT PLANNING
4

## Slide 5
SOFTWARE METRICS
Why Do We Need Software Metrics?
1
Objective Assessment
Replaces guesswork and subjective judgement with quantifiable, repeatable data about the software and process.
2
Better Estimation
Historical metrics (size, effort, defects) feed cost and schedule estimation models such as COCOMO.
3
Quality Control
Metrics such as defect density and complexity help identify weak modules before they fail in the field.
4
Process Improvement
Tracking process metrics over time reveals bottlenecks and supports continuous improvement (e.g., CMM).
5
Progress Tracking
Project metrics let managers monitor schedule, effort, and cost variance against the plan.
6
Informed Decision Making
Gives management the data needed to make realistic commitments to customers and stakeholders.
SOFTWARE PROJECT PLANNING
5

## Slide 6
CLASSIFICATION
Three Types of Software Metrics
Metrics are broadly classified according to what they measure: the product being built, the process used to build it, or the project undertaken to build it.
P
Product Metrics
Describe characteristics of the software product itself — size, complexity, design features, performance, quality.
Pr
Process Metrics
Focus on the effectiveness and efficiency of the process used to produce the software — used for long-term improvement.
Pj
Project Metrics
Describe project characteristics and execution — effort, cost, staffing, schedule — used by managers to adjust the plan.
SOFTWARE PROJECT PLANNING
6

## Slide 7
TYPES OF METRICS — PRODUCT
Product Metrics
Product metrics measure characteristics of the software product at any stage of its development — from requirements through delivered code.
Common Product Metrics
Size metrics —
Lines of Code (LOC), Function Points
Complexity metrics —
McCabe's Cyclomatic Complexity
Halstead's Software Science —
length, volume, effort measures
Quality metrics —
defect density, reliability, correctness
Design metrics —
coupling, cohesion, fan-in/fan-out
What They Help Assess
Understandability and readability of the code
Maintainability and ease of future modification
Complexity and hence likely error-proneness
Reusability of modules and components
Overall size, used as an input to cost and effort estimation models
SOFTWARE PROJECT PLANNING
7

## Slide 8
TYPES OF METRICS — PROCESS
Process Metrics
Process metrics are collected across all projects and over long periods of time to enable assessment and improvement of the software process itself.
Purpose
Used strategically, focusing on improving the software process over the long term rather than a single project.
Help an organization determine where its process is strong and where it needs improvement.
Provide a basis for models like the Capability Maturity Model (CMM) that grade process maturity.
Are often kept confidential to individual teams to avoid misuse for personnel evaluation.
Typical Examples
Effort and time spent in each phase (requirements, design, coding, testing)
Errors found per review / inspection hour
Defects discovered before and after release
Time required to fix a reported defect
Productivity — output (e.g., LOC or FP) per person-month
Number of change requests over time
SOFTWARE PROJECT PLANNING
8

## Slide 9
TYPES OF METRICS — PROJECT
Project Metrics
Project metrics describe project characteristics and execution and are used by a project manager and software team to adapt project workflow and technical activities.
Purpose
Used tactically, to track and adjust a single, ongoing project.
Applied to minimize the development schedule by making the necessary adjustments to avoid delays.
Used to assess product quality on an ongoing basis, and where necessary, modify the technical approach.
Collected on every project and combined with other projects' data to become part of process metrics.
Typical Examples
Number of developers and their effort (person-months)
Actual cost incurred versus budgeted cost
Schedule — actual progress versus planned milestones
Staffing pattern across the project timeline
Number of errors uncovered during each phase
Size of the software being produced
SOFTWARE PROJECT PLANNING
9

## Slide 10
SIZE ESTIMATION
Estimating the Size of Software
Because a project's cost and schedule are largely driven by the size of the software to be built, accurate size estimation is the starting point of every estimation model.
01
Lines of Code (LOC)
Counts the number of executable source lines to gauge program size directly.
02
Function Count (FP)
Counts functional features of the software (inputs, outputs, files, inquiries) independent of language.
03
Halstead's Software Science
Uses counts of operators and operands to derive length, volume, effort and related measures.
SOFTWARE PROJECT PLANNING
10

## Slide 11
SIZE ESTIMATION
Lines of Code (LOC)
LOC is one of the earliest and simplest size-oriented metrics — the size of a program is estimated by counting the number of source lines of code, once the project is complete (or estimated in advance by comparison with similar past projects).
How It Is Used
Estimators compute the size of software by comparing a new project to similar past projects with known LOC.
Once size (LOC) is estimated, it directly drives derived metrics such as Errors/KLOC, Defects/KLOC, Cost/LOC, and Documentation pages/KLOC.
KLOC = thousand (kilo) lines of code, the common unit for large systems.
Limitations
Depends heavily on the programming language — the same functionality can need very different LOC in different languages.
Cannot be measured accurately until the project is well underway or complete, weakening it for early estimation.
Rewards verbose code and penalises efficient, compact code, giving a misleading productivity picture.
Does not account for the complexity of the logic, only the physical size.
SOFTWARE PROJECT PLANNING
11

## Slide 12
SIZE ESTIMATION
Function Count (Function Point Analysis)
Function-Based metrics use Function Points (FP), derived from countable, function-oriented characteristics of the software — independent of the programming language used.
Five Information Domain Values
Number of External Inputs (EI) —
user inputs that provide distinct data to the software
Number of External Outputs (EO) —
derived data leaving the system (reports, messages)
Number of External Inquiries (EQ) —
interactive inputs requiring an immediate response
Number of Internal Logical Files (ILF) —
logical data groups maintained within the system
Number of External Interface Files (EIF) —
data groups used by the system but maintained by another
Computing Function Points
Step 1 — Each domain value is counted and classified as Simple, Average, or Complex, and multiplied by an empirically-derived weighting factor. Step 2 — The weighted counts are summed to give the Count Total (unadjusted FP). Step 3 — FP = Count Total × [0.65 + 0.01 × Σ(Fi)]
where Fi (i = 1 to 14) are complexity adjustment values based on factors such as data communication, performance, reusability, and operational ease.
SOFTWARE PROJECT PLANNING
12

## Slide 13
SIZE ESTIMATION
Halstead's Software Science
Maurice Halstead proposed that a program can be measured by counting operators and operands — a purely analytical approach to defining measures of software complexity.
Basic Counts
n1 Number of distinct operators appearing in the program
n2 Number of distinct operands appearing in the program
N1 Total number of operator occurrences (with repetition)
N2 Total number of operand occurrences (with repetition)
Operators & Operands
Operators: keywords, symbols, and function calls that act on data — e.g. +, -, if, while, =
Operands: variables and constants that represent data — e.g. x, count, 10, "total"
Two Base Measures
Program Vocabulary:
n = n1 + n2
Program Length:
N = N1 + N2
SOFTWARE PROJECT PLANNING
13

## Slide 14
SIZE ESTIMATION
Halstead's Derived Measures
Program Volume
V = N × log2(n)
Number of bits required to represent the program; reflects the size of the implementation.
Program Level
L = V* / V
Indicates how concisely the program is written relative to the theoretical minimum volume V*.
Program Difficulty
D = (n1/2) × (N2/n2)
Estimates how difficult the program is to write or understand.
Programming Effort
E = V / L = D × V
Estimated mental effort required to develop the program; used to estimate development time.
Estimated Time
T = E / S
S ≈ 18 (Stroud number, mental discriminations per second); gives estimated time to implement.
Estimated Bugs
B = E^(2/3) / 3000
Estimates the number of delivered bugs likely to remain in the software.
SOFTWARE PROJECT PLANNING
14

## Slide 15
COST ESTIMATION
The Need for Cost Estimation
Software cost/effort estimation is the process of predicting the effort, time, and money required to build a software system — one of the most difficult and important activities in project planning.
1
Enables management to make a realistic bid or budget commitment to a customer before development begins.
2
Allows the project manager to plan staffing levels, schedules, and resource allocation.
3
Provides a baseline against which actual progress and cost can be tracked and controlled.
4
Helps avoid cost/schedule overruns, one of the leading causes of software project failure.
5
Supports informed trade-off decisions between scope, cost, schedule, and quality.
SOFTWARE PROJECT PLANNING
15

## Slide 16
COST ESTIMATION
Cost Estimation Models
Once the size of the software is estimated, one or more estimation models can be used to translate that size into effort, cost, and schedule.
1
Empirical Estimation Models
Use data from past projects, expressed as an algorithmic relationship (e.g., COCOMO). The most widely used approach in practice.
2
Decomposition Techniques
Break the project into smaller functions or tasks and estimate each individually — e.g. LOC-based or FP-based decomposition.
3
The COCOMO Model
Constructive Cost Model by Barry Boehm — an empirical model widely used to estimate effort, cost and schedule based on size and cost drivers.
SOFTWARE PROJECT PLANNING
16

## Slide 17
COCOMO
COCOMO — Constructive Cost Model
Proposed by Barry W. Boehm (1981), COCOMO estimates effort (in person-months) and development time as a function of the estimated size of the software, expressed in KLOC (thousands of lines of code).
COCOMO Classifies Software Projects Into Three Modes
Organic Mode
Small teams with good experience working on well-understood, in-house applications with flexible requirements. E.g., simple business/data-processing systems.
Typical size: ≤ 50 KLOC
Semi-Detached Mode
A mixture of experienced and inexperienced staff working on a project with a mix of rigid and flexible requirements. E.g., utility programs, compilers.
Typical size: ≤ 300 KLOC
Embedded Mode
Projects with tight constraints (hardware, software, operational) and complex interfaces, often novel and demanding. E.g., real-time, flight control systems.
Typical size: Any size
SOFTWARE PROJECT PLANNING
17

## Slide 18
COCOMO
COCOMO — Basic Model
The simplest of the three COCOMO levels. It computes effort and cost as a function of program size expressed in estimated KLOC, using a small set of mode-specific constants.
Effort: E = a × (KLOC)^b person-months Development Time: D = c × (E)^d months
Project Mode | a | b | c | d
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi-Detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32
Notes
KLOC = estimated size of the project in thousands of delivered source lines
a, b, c, d are constants determined by project mode (Organic / Semi-detached / Embedded)
The Basic model gives a quick, rough estimate of project effort and cost, but does not account for differences in project attributes (e.g. reliability requirements, team experience) — that refinement is added in the Intermediate model.
SOFTWARE PROJECT PLANNING
18

## Slide 19
COCOMO
COCOMO — Intermediate Model
Refines the Basic model by adding a set of Cost Drivers — 15 attributes that adjust the nominal effort up or down based on product, hardware, personnel and project attributes.
Effort: E = a × (KLOC)^b × EAF person-months
EAF (Effort Adjustment Factor) = product of the ratings of all 15 cost drivers, each rated on a scale from Very Low to Extra High.
Product Attributes
Required reliability (RELY), Database size (DATA), Product complexity (CPLX)
Hardware Attributes
Execution time constraint (TIME), Main storage constraint (STOR), Virtual machine volatility (VIRT), Turnaround time (TURN)
Personnel Attributes
Analyst capability (ACAP), Programmer capability (PCAP), Applications experience (AEXP), Virtual machine experience (VEXP), Language experience (LEXP)
Project Attributes
Use of modern practices (MODP), Use of software tools (TOOL), Required schedule (SCED)
SOFTWARE PROJECT PLANNING
19

## Slide 20
SUMMARY
Key Takeaways
1
Software project planning depends on reliable metrics to estimate size, effort, cost and schedule before and during development.
2
Metrics fall into three categories — Product, Process, and Project — each serving a different purpose in planning and control.
3
Size can be estimated using Lines of Code, Function Point (Function Count), or Halstead's Software Science measures.
4
Halstead's measures derive length, volume, difficulty, effort, time and estimated bugs from operator/operand counts.
5
Cost estimation is essential for realistic budgeting; COCOMO is the most widely used empirical estimation model.
6
COCOMO's Basic model gives a quick estimate from size alone; the Intermediate model refines it with 15 cost drivers (EAF).
Thank You